## Master_Schedule
Milestone_ID | Process_Stage | Start_Date | End_Date | Assigned_Venue | Responsible_Lead | Status
M101 | Project Deliverable Submission | 2026-10-10 | 2026-10-25 | Online Portal | Prof. Ramesh Verma | Active (Cutoff 25 Oct)
M102 | Initial Screener & Compliance | 2026-10-26 | 2026-10-27 | Dept Office | Dr. S. K. Narayanan | Pending
M103 | Faculty Peer Review | 2026-10-28 | 2026-10-31 | Virtual Panels | Review Committee | Ripple Impacted
M104 | Score Compilation & Evaluation | 2026-11-01 | 2026-11-03 | Exam Wing | Academic Registrar | Senate Overlap Risk
M105 | Final External Viva Voce Defense | 2026-11-05 | 2026-11-08 | Lab 302 AI Center | External Examiners | Defense Bottleneck